# Cover Page

Abstract

Table of Contents

1. Progress Report	5

1.1. Introduction	5

1.1.1 Background	5

1.1.2 Challenges	5

1.1.3 Aims & Objectives	6

1.2. Research	8

1.3. Solutions	12

1.4. Project Management	14

1.4.1 Task breakdown	14

1.4.2 Time Assessment	18

1.4.3 Risk Analysis	21

1.5 References	22

Appendix A	22

2. Implementation	23

2.1 Project Progression	23

2.2 Changes to the Schedule	23

2.3 Learned From Milestones	23

2.4 Difficulties	23

2.5 Implementation Backup Plans	23

3. Reflections and Conclusion	24

3.1 Evaluation	24

3.2 Reflections	24

3.3 Future Expansion	24

4. References	25

5. Bibliography	26

6. Appendices	27

# 1. Progress Report

## 1.1. Introduction

### 1.1.1 Background

Splox Racers is a 3D sandbox racer created as the major project of the Southampton Solent University. The tracks will be generated on splines. Those splines can be created by the developer or a random generator and can be saved to the disk to load at a different time. The AI uses the splines as a guideline to figure out, how to drive along the track. Different points on the spline have different attributes to make different areas, like boosters or obstacles, on the track available. Each point also has attributes to control the tracks banking, thickness, width and whether or not it has guard rails available.

The players can build their own cars via a sandbox editor. There will be different block shapes available to create the chassis in any form. Blocks can be coloured to further improve the look of the car. Special blocks will be needed to change the cars behaviour, like speed, handling and so forth.
The editor makes sure, that the car has all necessary parts, exactly one seat, wheels and an engine.
Players can test their cars in a special track or a chosen/generated track to help fine-tune the cars behaviour.
If they are happy with the car, they can name it, save it and choose to drive it in races.

As of my research, no one ever combined a random spline track generator and a vehicle builder into a racing game.

### 1.1.2 Challenges

There will be quite a lot of challenges to overcome.

The mesh of the track has to be generated, so there are no holes or other artefacts in it and all the textures line up without any seems.

The random generator has to generate valid tracks by making sure the spline does not overlap itself and keeps enough distance, so that cars will not be blocked by the track. Loops have to be placed in a way that the players can build up enough speed to be able to make it through the loop. Obstacles have to be placed in a way that makes them fun i.e. make sure the distance between obstacles is not too low, as that will make the track boring, and not too high, as that will make the track too frustrating.

The car editor has to be easy to use and make sure the build cars are always valid. Therefore, it has to check for disconnected blocks and indicate them to the player. It has to make sure the player places all the mandatory parts and constraint the placement of blocks to keep the cars size to a certain maximum size.

Another challenge will be for the AI to drive along the spline in an intelligent way. Cars controlled by the AI have to be able to avoid obstacles.
They also need to be able to drive cars created by users without knowing how the car behaves in terms of acceleration, max speed and handling.

### 1.1.3 Aims & Objectives

The main aims are:

- Implementing a sandbox racing game

- Create a racing track on top of splines

The main objectives are:

- Create car editor

- Create splines

- Generate track on splines

- Combine previous objectives into one game

- Implement racing game rules

## 1.2. Research

The YouTuber DokipenTech [1] created an unreal engine 4 tool to create a road from a spline as shown in figure 1. He made four video tutorials about how he has done it using blueprints.
In addition, an employee of Epic made a live training [2], which is still available on YouTube. In that training video they show a sophisticated way to create meshes on splines, also using unreal engine 4 blueprints. See figure 2 for a preview of his work.

Figure 1: Road created on a spline with the unreal engine 4.

Figure 2: Spline road as created in a live training from Epic.

A sandbox vehicle editor has been done by several developers. Freejam LTD uses it in the game Robocraft [3] as seen in figure 3. Other games like Autocraft developed by Alientrap Games [4] also have the ability to create vehicles in a sandbox mode (see figure 4), though Autocraft does not use an external editor, just a mode switch in the current loaded level.
Another game that allows the player to create vehicles using blocks is Space Engineers by KEEN SWH LTD [5]. Space Engineers also does not switch into a separate editor and does not switch to a different mode to build as seen in figure 5.

Figure 3: Robot builder used in the game Robocraft.

Figure 4: Building mode in the game Autocraft.

Figure 5: Building a car in Space Engineers.

I could not find any implementation details of their editors. Therefore all information I have are from images and trying them out to get a feel of their functionality and controls.

## 1.3. Solutions

I will use the Unreal Engine 4 to implement the game, as it already provides helpful tools to expand upon. It already has built-in spline components and a sophisticated car controller to use as a base for the project.

To give players the ability to create their own cars, I will provide them with a separate editor mode as it is done in Robocraft. This allows me to constraint the cars size and make sure it is valid before it will be used to race. A separate editor makes also makes it easier to come back later and edit previously created cars.
There will be a virtual 3D-grid to place the blocks on and the editor will provide the player with a starting block. The player will only be able to place blocks attached on any other block and not free floating in the air. If they remove a block from the car, all blocks neighbouring the removed one will check if they still have a connection to the seat block. I will implement the check with a 3D version of the A* algorithm [6], which will find a way to the seat block if there is one. If there is not a route, it will notify the player by tinting the block red.

To create the spline roads, I will follow the tutorials mentioned before and extend upon it. The tutorials only show the basics to make it work, but there is more work needed to make it look “good” and to make sure that curves cannot be too steep. Furthermore, I decided to switch from blueprints to C++ as the extensions to the road generator will get very complex very fast if done in blueprints.

The AI will at first just use the spline as a path to drive on and will calculate the optimal speed by the steepness of curved, which it will detect through the angle of the tangent of a spline node point. They will drive along the spline using the steering algorithm, which also makes sure they avoid collisions.
Later in the development I plan to improve the AI so that it calculates a better path and better detect the optimal speeds also taking into consideration the cars specs.

## 1.4. Project Management

### 1.4.1 Task breakdown

I created tasks for the different parts of the game (see table 1). Everything to do with the track generator gets an ID starting with TG, car editor tasks have an ID starting with CE, the AI tasks begin with AI, asset tasks with AS and lastly the tasks which combine all the different parts into a game got IDs starting with GA. In addition, I gave each task a priority to indicate whether a feature is necessary (must have), will improve the game further (should have) or are entirely optional and might not be implemented due to the time needed to implement the game. In the task table, I also provided dependency to show which tasks have to be implemented in order to implement a certain other task. This ensures a smooth workflow, as I will not start tasks that cannot be completed at that point of work. Lastly, I provided a simple description of the task and what its implementation is supposed to achieve.

| ID | Priority | Dependency | Description |
| --- | --- | --- | --- |
| TG001 | Must Have |  | Generate the road mesh along the spline |
| TG002 | Must Have | TG001 | Apply road texture to road mesh |
| TG003 | Optional | TG001 | Make looping’s possible |
| TG011 | Must Have | TG001 | Add attributes to spline points to control width, thickness, bank and element type |
| TG012 | Must Have | TG011 | Add a start line onto the track |
| TG013 | Must Have | TG011 | Add goal line onto the track |
| TG014 | Should Have | TG011 | On closed loop make start to also be goal |
| TG015 | Should Have | TG011 | Add booster to speed up car when they are on it |
| Completed up to here |  |  |  |
| TG101 | Optional | TG001 | Randomly generate spline |
| TG102 | Optional | TG101 | Randomly change spline point attributes |
| CE001 | Must Have |  | Level to build car in |
| CE002 | Must Have | CE001 | UI for editor |
| CE003 | Must Have | CE001 | Place start block which can't be removed |
| CE004 | Must Have | CE001 | Let the player place blocks on other blocks |
| CE005 | Must Have | CE004 | Let the player delete placed blocks |
| CE006 | Must Have | CE005 | Check for car validity |
| CE011 | Must Have | CE001 | Let player select block types from menu |
| CE012 | Should Have | CE011 | Add different weight chassis blocks |
| CE013 | Must Have | CE011 | Add wheels |
| CE014 | Should Have | CE011 | Add engines |
| CE015 | Optional | CE011 | Add fuel tanks |
| CE021 | Should Have | CE011 | Add colour picker |
| CE022 | Should Have | CE021 | Colour chassis blocks |
| CE031 | Must Have | CE002 | Allow naming of car |
| CE032 | Must Have | CE006 | Allow saving of car to a file |
| CE033 | Must Have | CE032 | Allow loading of car from a file |
| CE041 | Optional | CE033 | Test drive car |
| CE051 | Optional | CE032 | Bake car data to use less colliders and meshes |
| GA001 | Must Have | TG;CE | Main Menu |
| GA002 | Must Have | GA001 | Car selection |
| GA003 | Must Have | GA001 | Level selection |
| GA011 | Must Have | GA002;GA003 | Load Level |
| GA012 | Must Have | GA011 | Spawn player |
| GA013 | Must Have | GA012 | Controls |
| GA014 | Should Have | GA011;AI | Spawn AI |
| GA015 | Must Have | GA013 | Win condition |
| GA021 | Must Have | GA011 | UI |
| GA022 | Must Have | GA021 | Show speed |
| GA023 | Should Have | GA021 | Show lap/laps |
| GA024 | Should Have | GA021;GA012;GA014 | Show place |
| AI001 | Should Have | GA | AI cars drive along spline |
| AI002 | Optional | AI001 | Avoid collisions with other cars |
| DC001 | Must Have |  | Create task list |
| DC002 | Must Have |  | Project proposal |
| DC003 | Must Have | DC001;DC002 | Progress report |
| DC011 | Must Have | DC003;GA | Final report |
| AS001 | Must Have |  | Road mesh and texture |
| AS002 | Must Have | AS001 | Start mesh and texture |
| AS003 | Should Have | AS002 | Goal mesh and texture |
| AS011 | Must Have |  | Chassis block mesh and texture |
| AS012 | Must Have |  | Wheel mesh and texture |
| AS013 | Should Have |  | Engine block mesh and texture |
| AS014 | Should Have |  | Fuel tank mesh and texture |
| AS021 | Must Have |  | UI textures |

Table 1: Task list with IDs, priority, task dependencies and descriptions.

### 1.4.2 Time Assessment

I estimated the time each task will take to be implement. For that, I created another table that shows the tasks category, ID and time estimate. The very last row is the sum of the time each task will need to be completed. The overall time estimate for all tasks amounts to 411 hours of work time, presumed there will not be any major problems or difficult to find errors, who increase the tasks time much.

| Track Generator |  | Car Editor |  | Game |  | AI |  | Assets |  | Documents |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task | Time | Task | Time | Task | Time | Task | Time | Task | Time | Task | Time |
| TG001 | 30,0 h | CE001 | 15,0 h | GA001 | 4,0 h | AI001 | 8,0 h | AS001 | 5,0 h | DC001 | 4,0 h |
| TG002 | 5,0 h | CE002 | 15,0 h | GA002 | 4,0 h | AI002 | 10,0 h | AS002 | 2,0 h | DC002 | 6,0 h |
| TG003 | 8,0 h | CE003 | 6,0 h | GA003 | 4,0 h |  |  | AS003 | 1,0 h | DC003 | 8,0 h |
| TG011 | 20,0 h | CE004 | 8,0 h | GA011 | 2,0 h |  |  | AS011 | 2,0 h | DC011 | 12,0 h |
| TG012 | 15,0 h | CE005 | 3,0 h | GA012 | 1,0 h |  |  | AS012 | 6,0 h |  |  |
| TG013 | 10,0 h | CE006 | 20,0 h | GA013 | 3,0 h |  |  | AS013 | 3,0 h |  |  |
| TG014 | 6,0 h | CE011 | 7,0 h | GA014 | 2,0 h |  |  | AS014 | 2,0 h |  |  |
| TG015 | 6,0 h | CE012 | 2,0 h | GA015 | 1,0 h |  |  | AS021 | 6,0 h |  |  |
| TG101 | 30,0 h | CE013 | 6,0 h | GA021 | 3,0 h |  |  |  |  |  |  |
| TG102 | 10,0 h | CE014 | 2,0 h | GA022 | 1,0 h |  |  |  |  |  |  |
|  |  | CE015 | 2,0 h | GA023 | 1,0 h |  |  |  |  |  |  |
|  |  | CE021 | 16,0 h | GA024 | 2,0 h |  |  |  |  |  |  |
|  |  | CE022 | 3,0 h |  |  |  |  |  |  |  |  |
|  |  | CE031 | 1,0 h |  |  |  |  |  |  |  |  |
|  |  | CE032 | 8,0 h |  |  |  |  |  |  |  |  |
|  |  | CE033 | 8,0 h |  |  |  |  |  |  |  |  |
|  |  | CE041 | 10,0 h |  |  |  |  |  |  |  |  |
|  |  | CE051 | 36,0 h |  |  |  |  |  |  |  |  |
| 140,0 h |  | 168,0 h |  | 28,0 h |  | 18,0 h |  | 27,0 h |  | 30,0 h |  |

Table 2: Time estimation to complete every individual task.

Since the car editor is the biggest feature of the game, it will also take the most time to complete. CE001 and CE002 have gotten a bigger amount of time than most tasks in the car editor category, since they provide the basic for the entire car editor and everything builds up on those. CE006, which is the car validity checker, has also gotten a large amount of time allocated, since it has to be very efficient as it might get executed several times per frame and should not increase the frame time by a noticeable amount. To implement and optimize the algorithm to the desired degree will take a long time, which is why the allocated time is set to 20 hours.
The largest time allocated to the car editor is the mesh and collider baking of the car, which will decrease computation and render times in the races considerably. It is also set to optional, since it might not be implemented in the time I have gotten to complete the game. It will implemented last, if there is time left, or after the project submission.

The second biggest category is the track generator. Again the first task has the longest time allocated to it, since it will provide the basis for each other task to build upon. TG101 and TG102 are also optional tasks, which might not be implemented, since they will need a lot of work and fine-tuning, but are not necessary for the game to function properly.

The basic implementation of the AI will probably not take longer than 18 hours, since they will only drive along the spline, which is already given and try to avoid other cars, which should not be much of a problem using the steering algorithm.

Assets will mostly be gathered from free sources or created by myself; they will be plain looking assets, as they are not necessary for the games functionality. They will be improved after the project submission.

The Game category will consist of the combination of all other categories and also provide menus, win conditions, detection of the games states and so on. Combining the previous parts should go rather quickly, since they already have everything necessary to load the correct data.

### 1.4.3 Risk Analysis

To prevent the loss of the project due to technical errors, I am using version control. I am using GitHub as a version control service (See Appendix A for the link). This allows me to keep a copy on a different server and it allows me to revert changes to the code that may cause errors in the game.

To make sure, the game will reach a certain point of completion in that it can actually be player, I will complete the task according to their priorities and dependencies. Task with the priority of optional will be done as the very last, since they are high risk and do not provide enough return to do them earlier.
The “Must Have”-priority tasks are the ones to provide a huge return and should therefore be completed at first.

Code optimization and AI improvements are not listed in the task list, since they will only be done if there is time left, after all other tasks have been completed, since especially the optimization may break a lot of code and is therefore very high risk.
Changes to the AI will change the entire game balance and experience and should be thoroughly tested, which will cost a lot of time.

## 1.5 References

[1] Unreal engine 4 road tool in blueprints with Spline and SplineMesh - part 1 Spline components, 2014 . YouTube

[2] Using Splines & Spline components | live training | unreal engine, 2014 . YouTube

[3] MIKECODEJAMMER and FREEJAM LTD, 2017. ROBOCRAFT [viewed 3 March 2017]. Available from: http://robocraftgame.com/

[4] ALIENTRAP GAMES, n.d. Autocraft - early alpha access [viewed 3 March 2017]. Available from: http://www.autocraftgame.com/

[5] KEEN SWH LTD, 2013. Space engineers [viewed 3 March 2017]. Available from: http://www.spaceengineersgame.com/

[6] Cui, X. and Shi, H., 2011. A*-based pathfinding in modern computer games. International Journal of Computer Science and Network Security, 11(1), pp.125-130.

## Appendix A

Link to the GitHub repository: https://github.com/NeoIzen/SploxRacers

# 2. Implementation

## 2.1 Project Progression

Methodologies: agile, task breakdown, Prototyping, react to changes rather than planning

Order of tasks completion / Diary

## 2.2 Changes to the Schedule

When things did not work out (vehicle, garbage collector bug, Road tool too big for blueprint)

## 2.3 Learned From Milestones

Milestones to consider: 
- Car editor
- Track tool
- Game

Things that appear easy can be difficult to accomplish -> plan for more time

## 2.4 Difficulties

Garbage collector bug
Vehicle movement not working as needed
NewObject from template object instead of configured blueprint

## 2.5 Implementation Backup Plans

Creating an own vehicle system

# 3. Reflections and Conclusion

## 3.1 Evaluation

## 3.2 Reflections

## 3.3 Future Expansion

Improving design
Adding more block types
tweaking spline
improve assets
multiplayer
usable items
Car destruction

# 4. References

# 5. Bibliography

# 6. Appendices