## Task List
Must Have
Should Have | ID | Type | Dependency | Description
Optional | TG001 | Must Have |  | Generate the road mesh along the spline
| TG002 | Must Have | TG001 | Apply road texture to road mesh
| TG003 | Optional | TG001 | Make loopings possible
| TG011 | Must Have | TG001 | Add attributes to spline points to control width, thickness, bank and element type
| TG012 | Must Have | TG011 | Add a start line onto the track
| TG013 | Must Have | TG011 | Add goal line onto the track
| TG014 | Should Have | TG011 | On closed loop make start to also be goal
| TG015 | Should Have | TG011 | Add booster to speed up car when they are on it
| TG101 | Optional | TG001 | Randomly generate spline
| TG102 | Optional | TG101 | Change spline point attributes
| CE001 | Must Have |  | Level to build car in
| CE002 | Must Have | CE001 | UI for editor
| CE003 | Must Have | CE001 | Place start block which can't be removed
| CE004 | Must Have | CE001 | Let the player place blocks on other blocks
| CE005 | Must Have | CE004 | Let the player delete placed blocks
| CE006 | Must Have | CE005 | Check for car validity
| CE011 | Must Have | CE001 | Let player select block types from menu
| CE012 | Should Have | CE011 | Add different weight chassis blocks
| CE013 | Must Have | CE011 | Add wheels
| CE014 | Should Have | CE011 | Add engines
| CE015 | Optional | CE011 | Add fuel tanks
| CE021 | Should Have | CE011 | Add colour picker
| CE022 | Should Have | CE021 | Colour chassis blocks
| CE031 | Must Have | CE002 | Allow naming of car
| CE032 | Must Have | CE006 | Allow saving of car to a file
| CE033 | Must Have | CE032 | Allow loading of car from a file
| CE041 | Optional | CE033 | Test drive car
| CE051 | Optional | CE032 | Bake car data to use less colliders and meshes
| GA001 | Must Have | TG;CE | Main Menu
| GA002 | Must Have | GA001 | Car selection
| GA003 | Must Have | GA001 | Level selection
| GA011 | Must Have | GA002;GA003 | Load Level
| GA012 | Must Have | GA011 | Spawn player
| GA013 | Must Have | GA012 | Controls
| GA014 | Should Have | GA011;AI | Spawn AI
| GA015 | Must Have | GA013 | Win condition
| GA021 | Must Have | GA011 | UI
| GA022 | Must Have | GA021 | Show speed
| GA023 | Should Have | GA021 | Show lap/laps
| GA024 | Should Have | GA021;GA012;GA014 | Show place
| AI001 | Should Have | GA | AI cars drive along spline
| AI002 | Optional | AI001 | Avoid collisions with other cars
| DC001 | Must Have |  | Create task list
| DC002 | Must Have |  | Project proposal
| DC003 | Must Have | DC001;DC002 | Progress report
| DC011 | Must Have | DC003;GA | Final report
| AS001 | Must Have |  | Road mesh and texture
| AS002 | Must Have | AS001 | Start mesh and texture
| AS003 | Should Have | AS002 | Goal mesh and texture
| AS011 | Must Have |  | Chassis block mesh and texture
| AS012 | Must Have |  | Wheel mesh and texture
| AS013 | Should Have |  | Engine block mesh and texture
| AS014 | Should Have |  | Fuel tank mesh and texture
| AS021 | Must Have |  | UI textures

## Time plan
| Track Generator |  | Car Editor |  | Game |  | AI |  | Assets |  | Documents
| Task | Time | Task | Time | Task | Time | Task | Time | Task | Time | Task | Time
| TG001 | 30 | CE001 | 15 | GA001 | 4 | AI001 | 8 | AS001 | 5 | DC001 | 4
| TG002 | 5 | CE002 | 15 | GA002 | 4 | AI002 | 10 | AS002 | 2 | DC002 | 6
| TG003 | 8 | CE003 | 6 | GA003 | 4 |  |  | AS003 | 1 | DC003 | 8
| TG011 | 20 | CE004 | 8 | GA011 | 2 |  |  | AS011 | 2 | DC011 | 12
| TG012 | 15 | CE005 | 3 | GA012 | 1 |  |  | AS012 | 6
| TG013 | 10 | CE006 | 20 | GA013 | 3 |  |  | AS013 | 3
| TG014 | 6 | CE011 | 7 | GA014 | 2 |  |  | AS014 | 2
| TG015 | 6 | CE012 | 2 | GA015 | 1 |  |  | AS021 | 6
| TG101 | 30 | CE013 | 6 | GA021 | 3
| TG102 | 10 | CE014 | 2 | GA022 | 1
|  |  | CE015 | 2 | GA023 | 1
|  |  | CE021 | 16 | GA024 | 2
|  |  | CE022 | 3
|  |  | CE031 | 1
|  |  | CE032 | 8
|  |  | CE033 | 8
|  |  | CE041 | 10
|  |  | CE051 | 36
Accumulated Time: |  | 140 |  | 168 |  | 28 |  | 18 |  | 27 |  | 30 | 411